## Sheet1
Cinema
Buyers Module
Defect ID: | Release/Build # | Open Date: | Close Date: | Problem Area: | Defect or Enhancement: | Problem Title: | Problem Description: | Current Environment: | Defect Type: | Who Detected: | How Detected:
1 | SNP V2.00 | 2015-02-09 |  | Search Page | Defect | Displaying Places bar not hides | Search the cinema and it displays a list medias but when clicks not hides | Windows 7 | UX | QA | Testing
2 | SNP V2.00 | 2015-02-09 |  | Search Page | Defect | it accepts a media for the same campaign many times | Click on media and click on add a campaign Click on Use Existing. | Windows 7 | Functional | QA | Testing
3 | SNP V2.00 | 2015-02-09 |  | Search Page | Enhancement | Campaign popup add will show a mouse over | Click on any media and move the cursor to the add campaign | Windows 7 | UX | QA | Testing
4 | SNP V2.00 | 2015-02-09 |  | Campaign | Defect | Campaign list not shown any medias | Go to campaign and click on any campaign it shows empty list but in the campaign shows the medias. | Windows 7 | UX | QA | Testing
5 | SNP V2.00 | 2015-02-09 |  | Campaign | Enhancement | Archive campaign in actions Unachieved should be there | Archive campaign in actions Unachieved should be there | Windows 7 | UX | QA | Testing
6 | SNP V2.00 | 2015-02-09 |  | Campaign | Defect | In Campaign allows to campaign make live without any media | Create a new Campaign and in actions click on make live , it cant be accept | Windows 7 | Functional | QA | Testing
7 | SNP V2.00 | 2015-02-09 |  | Campaign | Defect | Campaign allows without for name is empty also to create a campaign | Click on Edit Campaign , Make a any field empty either For Name or Campaign Name. | Windows 7 | Functional | QA | Testing
8 | SNP V2.00 | 2015-02-09 |  | Campaign | Defect | Campaign list not showing Campaign name |  | Windows 7 | Functional | QA | Testing
9 | SNP V2.00 | 2015-02-09 |  | Campaign | Enhancement | In Archive list whatever list is there in the Plan , it should be displayed |  | Windows 7 | Functional | QA | Testing
10 | SNP V2.00 | 2015-02-09 |  | Search Page | Defect | In Home Page of Cinema module , when it comes first some code and after it will gives the List of medias |  | Windows 7 | Performance | QA | Testing
11 | SNP V2.00 | 2015-02-09 |  | Search Page | Defect | In movie schedule , Click on Upcoming Movies. it is not showing list | In this , Click on movie repeatedly. The popup of movies disturbs the design | Windows 7 | UX | QA | Testing
12 | SNP V2.00 | 2015-02-09 |  | Campaign | Enhancement | In the campaign list adding a campaign is not there | Click on campaign name we did not get a how to add a Theatre to the campaign. | Windows 7 | Functional | QA | Testing
13 | SNP V2.00 | 2015-02-09 |  | Home Page of CINEMA | Defect | In the home page of cinema footer is not added and images are not shown |  | Windows 7 | Functional | QA | Testing
14 | SNP V2.00 | 2015-02-09 |  | Search Page | Defect | Add to campaign shows a same display in next time also. | In the search page click any theatre and click on add a campaign . Now again click on add to campaign it opens a same popup | Windows 7 | Functional | QA | Testing
15 | SNP V2.00 | 2015-02-10 |  | Campaign | Defect | Campaign page GO Button is missing | Go to campaign page and after the search field GO Button is not there | Windows 7 | UX | QA | Testing
16 | SNP V2.00 | 2015-02-10 |  | Campaign | Enhancement | In Live Campaign unable to see theatres |  | Windows 7 | UX | QA | Testing
17 | SNP V2.00 | 2015-02-10 |  | Campaign | Defect | Campaign list page , searching for a theatre field after GO Button is missing | Go to campaign list page and after the search field GO Button is not there | Windows 7 | UX | QA | Testing
18 | SNP V2.00 | 2015-02-10 |  | Search Page | Defect | In The list view add a campaign for multiple theatres | Click on list in search page and click on check box for selected city and now change the city add a campaign. Now again come to the previous campaign the check boxes will still shows | Windows 7 | Functional | QA | Testing
19 | SNP V2.00 | 2015-02-10 |  | Campaign | Defect | Select a slot and position save button is not working | click on check box for multiple theatres now select actions for ad type and change now click on save | Windows 7 | UX | QA | Testing
20 | SNP V2.00 | 2015-02-10 |  | Campaign | Defect | In campaign date is completed but how it should be live |  | Windows 7 | Functional | QA | Testing
21 | SNP V2.00 | 2015-02-10 |  | Campaign | Defect | in the Campaign list , theatres Total Campaign Cost shows 0 Rs | Click on Campaign list and it have multiple theatres but the total cost will shows 0 Rs. | Windows 7 | Functional | QA | Testing
22 | SNP V2.00 | 2015-02-10 |  | Search Page | Defect | Campaign adds a previously selected no of theatres for selected city |  | Windows 7 | Functional | QA | Testing
23 | SNP V2.00 | 2015-02-10 |  | Campaign | Enhancement | In Campaign Page ,Screens and Seats are not we get . | Go to campaign page Here we have seats and screens fields instead of this Ad Type should be there. Why….? When we creating a new campaign its having Ad type and also we not valid calculating for no of screens and seats . | Windows 7 | UX | QA | Testing
24 | SNP V2.00 | 2015-02-10 |  | Search Page | Enhancement | In the theatre detail popup +add Campaign is there object overlapping | Go to Cinema search page and click on theatre in this | Windows 7 | UX | QA | Testing
25 | SNP V2.00 | 2015-02-11 |  | Search Page | Defect | Searching for theatre for both shows 59 , but the count for single screen 45 and multiplex 12 showing. |  | Windows 7 | UX | QA | Testing
26 | SNP V2.00 | 2015-02-11 |  | Campaign | Enhancement | not lookup for the live campaign for seeing Theatres |  | Windows 7 | UX | QA | Testing
27 | SNP V2.00 | 2015-02-11 |  | Campaign | Defect | If the campaign is live, the status is not shown it is active or pending or completed |  | Windows 7 | UX | QA | Testing
28 | SNP V2.00 | 2015-02-11 |  | Search Page | Defect | select for a different Ad Type Showing a same number of theatres |  | Windows 7 | UX | QA | Testing
29 | SNP V2.00 | 2015-02-11 |  | Search Page | Defect | For a Search page of Theatre search for Theatres in Chennai , Action field of Add to campaign shows different design. | Check the spelling of actions | Windows 7 | UX | QA | Testing
30 | SNP V2.00 | 2015-02-11 |  | Campaign | Defect | In search field , For Name should be there Instead of Client |  | Windows 7 | UX | QA | Testing
31 | SNP V2.00 | 2015-02-11 |  | Campaign | Defect | In the Campaign live , cities field having the theatre list and theatres shows empty |  | Windows 7 | Functional | QA | Testing
32 | SNP V2.00 | 2015-02-11 |  | Campaign | Defect | In the Campaign list , theatre Popup showing a empty theatres and Showing extra Check box |  | Windows 7 | UX | QA | Testing
33 | SNP V2.00 | 2015-02-11 |  | Campaign | Defect | In the Campaign list , theatre Popup save button no working and showing a network problem try again later |  | Windows 7 | UX | QA | Testing
34 | SNP V2.00 | 2015-02-11 |  | Login | Defect | Cinema Campaign path is not set and not linked to this account. | Here the cinema@gmail.com account is created for cinema module and now login with a valid details it opens old campaign list , but it should be Cinema Campaign list. | Windows 7 | Functional | QA | Testing
1 | SNP V2.00 | 2015-02-10 |  | Manage POI | Defect | Click on add a POI , add button not works. |  | windows7 | UX | QA | Testing
2 | SNP V2.00 | 2015-02-10 |  | Manage POI | Defect | Map is not displaying |  | windows7 | UX | QA | Testing
3 | SNP V2.00 | 2015-02-10 |  | Manage POI | Defect | List View is not available |  | windows7 | UX | QA | Testing
4 | SNP V2.00 | 2015-02-11 |  | Manage POI | defect | In Manage folder Popup , New folder instead of create a folder should be there | In Manage folder Popup , New folder instead of create a folder should be there and when click on New folder The design of the create folder not well | windows7 | UX | QA | Testing
5 | SNP V2.00 | 2015-02-11 |  | Manage POI | Enhancement | No need of after creating a POI and showing a Popup of ,Hi there, Create Point of Interest(POI) which will help you plane media campaign effectively. |  | windows7 | UX | QA | Testing
6 | SNP V2.00 | 2015-02-11 |  | Manage User | Defect | In Actions All Icons are Object Overlapping |  | windows7 | UX | QA | Testing
7 | SNP V2.00 | 2015-02-11 |  | Manage User | Defect | Adding a Image to the Profile Photo , not responding and not displays |  | windows7 | UX | QA | Testing
8 | SNP V2.00 | 2015-02-11 |  | Manage User | Defect | The Admin to admin send credential is not working |  | windows7 | Functional | QA | Testing
9 | SNP V2.00 | 2015-02-11 |  | Manage User | defect | In Edit User and add User Reporting to Scroll Bar Having the Design Problem |  | windows7 | UX | QA | Testing
10 | SNP V2.00 | 2015-02-11 |  | Account Settings | Defect | In Monitor setting alerts and Tags having a design Problem for Chrome browser |  | windows7 | UX | QA | Testing

## Sheet2
Defect ID: | Release/Build # | Open Date: | Close Date: | Problem Area: | Defect or Enhancement: | Problem Title: | Problem Description: | Current Environment: | Defect Type: | Who Detected: | How Detected: