## Sheet1
ANDROID MOBILE
Snapooh Monitor
Defect ID: | Release/Build # | Open Date: | Problem Area: | Defect or Enhancement: | Problem Title: | Problem Description: | Current Environment: | Defect Type: | Who Detected: | How Detected:
1 | SNP MON V1.4 | 2015-02-12 | Explorer | Enhancement | In the Explorer Captured , Uploaded and Expired Images shows no Images. | In the Explorer Captured , Uploaded and Expired Images shows no Images. It should be "Captured Images are empty " OR " No Images are Uploaded " | ANDROID 4.0ICS | UX | QA | Testing
2 | SNP MON V1.4 | 2015-02-12 | Explorer | Defect | Expired Image Do not have Monitored details (Corrupted) | If the is Expired , it also should have the details of monitored Image. Why…? Suppose user forget monitoring or linking for supposed media is expired and seeing the detail he will again will capture | ANDROID 4.0ICS | UX | QA | Testing
3 | SNP MON V1.4 | 2015-02-12 | Explorer | Defect | In the Location Icon field not shown the Details |  | ANDROID 4.0ICS | UX | QA | Testing
4 | SNP MON V1.4 | 2015-02-12 | Monitor Details | Defect | In the Monitor details Screen Time Stamp Not shown |  | ANDROID 4.0ICS | UX | QA | Testing
5 | SNP MON V1.4 | 2015-02-12 | Monitor Details | Defect | When showing Details of the Monitor details Location Overlapped. |  | ANDROID 4.0ICS | UX | QA | Testing
6 | SNP MON V1.4 | 2015-02-12 | Monitor Details | Defect | Monitor Details is not well Organised Place Media. | 1) ID Instead of Media ID 2) Media Type 3) Location should be there and Date is missing | ANDROID 4.0ICS | UX | QA | Testing
7 | SNP MON V1.4 | 2015-02-12 | Monitor Details | Defect | Monitor Details is not well Organised Street Media. | 1) ID Instead of Media ID 2) Media Type 3) Location should be there | ANDROID 4.0ICS | UX | QA | Testing
8 | SNP MON V1.4 | 2015-02-12 | Camera | Enhancement | When Click on camera Button it will Captures and again click it will Captures previously Captured image is neither saved nor deleted. | If Cancel Button is there to cancel why it cancels , when again clicking | ANDROID 4.0ICS | UX | QA | Testing
9 | SNP MON V1.4 | 2015-02-12 | Image Preview | Enhancement | The shown identify media to link etc not look like buttons. |  | ANDROID 4.0ICS | UX | QA | Testing
10 | SNP MON V1.4 | 2015-02-12 | Image Preview | Enhancement | When click on Identify media to link , shown buttons are look and feel and design of the popup is overlapping |  | ANDROID 4.0ICS | UX | QA | Testing
11 | SNP MON V1.4 | 2015-02-12 | Image Preview | Defect | When removing the all images in preview it shown empty . | Instead of this , A Message should be there | ANDROID 4.0ICS | UX | QA | Testing
12 | SNP MON V1.4 | 2015-02-12 | Link Monitor | Enhancement | When In the Icons like Alert , Tag and Notes when selection after any of these, colour of the Icon should change |  | ANDROID 4.0ICS | UX | QA | Testing
13 | SNP MON V1.4 | 2015-02-12 | Link Monitor | Defect | Click on Notes Icon keep on enter . The OK Button Disappears |  | ANDROID 4.0ICS | UX | QA | Testing
14 | SNP MON V1.4 | 2015-02-12 |  | Defect | Linked Monitor Images(In Offline State) is going to the Expired State | 1) Click on Airplane mode on 2) Capture the Image and link the monitor. 3) Now off the airplane mode and click on upload , it goes to expired date. | ANDROID 4.0ICS | Functional | QA | Testing
15 | SNP MON V1.4 | 2015-02-16 | Link Monitor | Defect | Alerts , Tags and notes are not linkable in offline mode. |  | ANDROID 4.0ICS | Functional | QA | Testing
16 | SNP MON V1.4 | 2015-02-16 | Uploading | Defect | Indoor media Id loading for Street Media (Manual) | Capture an Image In Selecting Street Media and Now Link manually with Indoor media ID . It accepting and uploads. | ANDROID 4.0ICS | Functional | QA | Testing
17 | SNP MON V1.4 | 2015-02-16 | Uploading | Enhancement | When Uploading a more then 5 images per monitor for 4 to 5 medias it will take approximately 25 min (Medium Image size) |  | ANDROID 4.0ICS | Performance issue | QA | Testing
18 | SNP MON V1.4 | 2015-02-16 | linking | Defect | unfortunately , Snapooh monitor has stopped. | 1) click on capture and select indoor media . 2) capture and select manually. 3) link the monitor ID 16894. 4) click on go. | ANDROID 4.0ICS | Functional | QA | Testing
19 | SNP MON V1.4 | 2015-02-16 | QR Code | Defect | second time not linked the QR code with media | 1) Select Indoor media and Capture a Image, Link the media With QR Code 245 and upload. 2) select indoor media and link the QR code 245 it is not selecting or linking a media | ANDROID 4.0ICS | Functional | QA | Testing
20 | SNP MON V1.4 | 2015-02-16 | Link Monitor | Defect | The monitor will be linked to ID instead of Monitor will be linked to QR Code. | Linking the QR Code to the Monitor. | ANDROID 4.0ICS | Functional | QA | Testing
Defect ID: | Release/Build # | Open Date: | Problem Area: | Defect or Enhancement: | Problem Title: | Problem Description: | Current Environment: | Defect Type: | Who Detected: | How Detected:
| V 1.4 | 2015-03-23 |  |  | Mon_V1.4:Image Preview: QR code linking with the url or contact etc… | 1. Go to Dashboard. 2. click on capture button. 3. Select 'Choose Category' and media type as Street media. 4. Capture a Image. 5. Select Identify media to link. 6. Click on QR code. 7. Scan the QR code with the URL Actual: Scanned QR Code is linked with the media and unable to upload Expected: QR Code should be restrict to the only Integers and msg should display in the Scanning the QR Code | Android ICS
1692 | V 1.4 | 2015-03-23 |  |  | Mon_V1.4:Link monitor: Place media is allowing the linking of the street media. | 1. Go to Dashboard. 2. click on capture button. 3. Select 'Choose Category' and media type as Street media. 4. Capture a Image. 5. Select Identify media to link. 6. Click on Manual. 7. Enter Place media ID or alias. Actual: Place media is displayed in the 'Link monitor' screen. Expected: It should be display a message media id is invalid. | Android ICS
1691 | V 1.4 | 2015-03-23 |  |  | Mon_V1.4:Link monitor: Alert or tags or notes popup is not displayed in the offline mode | Set mobile for offline mode(no data and gps) 1. Go to Dashboard. 2. click on capture button. 3. Select 'Choose Category' and media type as Street media. 4. Capture a Image. 5. Select Identify media to link. 6. Click on Manual. 7. Enter Place media ID or alias. 8. Click on alerts or tags or notes Icons. Actual: Alert or tags or notes popup is not displayed Expected: It should be display a alert or tag or notes popup. | Android ICS
1688 | V 1.4 | 2015-03-23 |  |  | Mon_V1.4:Link monitor: colour of the Icon not updated when alert or tag or notes updating. | Set mobile for offline mode(no data and gps) 1. Go to Dashboard. 2. click on capture button. 3. Select 'Choose Category' and media type as Street media. 4. Capture a Image. 5. Select Identify media to link. 6. Click on Manual. 7. Enter Place media ID or alias. 8. Click on alerts or tags or notes Icons. 9. Enter the Text in notes Actual: Alert or tags or notes Icons color is not changed Expected: It should be change the color of the icon when alert or tag or notes is updated. | Android ICS
1704 | V 1.4 | 2015-03-23 |  |  | Mon_V1.4:Help: all the screens are not updated as per app version. | 1. Go to help screen 2. Swipe to the 2nd screen. Actual: Screens are not updated in the help. Expected: all the screens are updated to the latest version of the application. | Android ICS
1705 | V 1.4 | 2015-03-23 |  |  | Mon_V1.4:Help: Percentile of loading screen shown but concept is not implemented . | 1. Go to help screen 2. Swipe to the last screen of the help. Actual: Percentile of loading screen shown but concept is not implemented . Expected: dash board should have the percentile of uploading monitors. | Android ICS
1771 | V 1.4 | 2015-03-23 |  |  | Mon_V1.4:Dashboard:medias are expiring when 24hr format is enabled. | 1. Go to mobile device settings. 2. select settings . 3. Select date and time. 4. Select the select the automatic date and time check box. 5. select Use 24-hour format check box. 6. Select Snapooh monitor. 7. Go to Dashboard. 8. click on capture button. 9. Select 'Choose Category' and media type as Street media. 10. Capture a Image. 11. Select Identify media to link. 12. Click on Manual. 13. Enter Place media ID or alias (set the device for offline mode) . 14. click on upload button. 15. Go to mobile device settings. 16. select settings . 17. Select date and time. 18. select the automatic date and time uncheck the check box. 19. select Use 24-hour format and uncheck the check box. 20. Select Snapooh monitor. 21. Go to Dashboard.(online). 22. click on upload button. Actual: all the monitors are transferred to captured state to expired state. Expected: all the monitors should be captured state. | Android ICS
1772 | V 1.4 | 2015-03-23 |  |  | Mon_V1.4:Image preview: detection of indoor medias place and place type is very slow. | 1. Go to Dashboard. 2. click on capture button. 3. Select 'Choose Category' and media type as place media. 4. Capture a Image. 5. Select Identify media to link. Actual :identifying of the mall and detecting of media taking a lot of time. Expected: Detecting of a place and place type should be load quickly. | Android ICS
1694 | V 1.4 | 2015-03-25 |  |  | Mon_V1.4:Unfortunately snapooh monitor stopped message is displayed. | 1. Go to Dashboard. 2. click on capture button. 3. Select 'Choose Category' and media type as place media. 4. Capture a Image. 5. Select Identify media to link. 6. Click on auto. 7. Select the floor and media type. Actual: When retrieving the media the application is crashed and showing a message of "unfortunately, snapooh monitor is stopped". Expected: it should be retrieve the all the monitors. Note: Please refer the same defect in the steps in capturing a image and uploading a monitor.
| V 1.4 | 2015-03-25 |  |  | Mon_V1.4:Link monitor: Linking a more then 2 monitors unable to upload. | 1. Go to Dashboard. 2. click on capture button. 3. Select 'Choose Category' and media type as indoor media. 4. Capture a Image. 5. Select Identify media to link. 6. Click on auto. 7. Select the floor and Click on 2 check box. 8. Click on upload button. Actual: the monitor with linked medias unable to upload. Expected: The 2 linked monitors should be upload.
| V 1.4 |  |  |  | Mon_V1.4:Image preview: Application is taking the last known location instead of the current location. | 1. Enable the mobile data 2. Go to Capture>choose Category(Street or Place) >capture a image>identify media to link 2. Click on auto . Actual: displays the following message "no media available for this location". Expected: application should identify medias and retrieve the data available for the current location
| V 1.4 |  |  |  | Mon_V1.4:Landmark or Place>auto>please choose a places Category: Application crashes and "unfortunately snapooh monitor stopped " message is displayed. | 1. Go to Capture>choose Category "Land mark or Place">Capture a Image>Identify media to link>auto: 2. Select any place type in the "Choose a places category". Actual: "unfortunately, Snapooh monitor has stopped" message is displayed. Expected: application should identify the selected place type media
| V 1.4 | 2015-03-26 |  |  | Mon_V1.4: Image Preview: Malls are detecting when Mall is deactivated in the Web application. | (Web application) 1. Go to medias>place media>PMM>actions: 2. Click on deactivate (Snapoh Monitor) 1. Go to Capture>choose category "indoor media">capture a image: 2. Select identify media to link. 3. Click on auto. Actual:popup is displayed with the deactivated mall is detected with the showing floor and media type . Expected: The deactivated mall should not detect and display a message " for this location no place is availble" Notes: if only one place is there message must be display and there are two places in the same radious the particular deactivated mall should not detect.

## APRIL
Defect ID: | Release/Build # | Open Date: | Problem Area: | Defect or Enhancement: | Problem Title: | Problem Description: | Current Environment: | Defect Type: | Who Detected: | How Detected:
| MO V1.4 | 2015-04-01 | Link monitor | Defect | Mon_V1.4:Capture>Choose a category> Capture an image> Identify media to link>Manual: The message displayed in the "link monitor" screen is incorrect. | 1. Go to Capture>Choose a category> Capture an image: 2. select identify media to link . 3. click on manual. 4. Enter an alphanum. 5. "Media not found . Proceed without linking" message . Click ok. Actual: The message is displayed with entered "alphanum" Expected: "this monitor will not be linked to any medias" message should display | Android ICS | Small
| MO V1.4 | 2015-04-02 |  | Suggestion | Mon_V1.4:Capture>Choose a category> Capture an image> Identify media to link>Manual: Restrict the digit or alphanum to the certain limit in the Manual selection of media Id | 1. Go to Capture>Choose a category> Capture an image: 2. select identify media to link . 3. click on manual. 4. Enter a 20 digit number . Actual: allows the special characters and more then 20 digits its accepting. Expected: It should be restrict the length of the id and allow certain character and digits only . Notes:-please restrict the special characters also | Android ICS | Small
| MO V1.4 | 2015-04-06 |  | dEFECT | MonV1.4: Qrcode: Medias are retrieved using media ID's as QR code | 1. Choose Place media as the category 2. Capture an image and save 3. Select Qrcode option to identify media to link 4. Enter 'media id' number in Qrcode generator 5. Scan the Qrcode Actual: The media retrieved has the 'media id' entered in the Qrcode generator Expected: The app must validate the QRcode and display a message informing that the qr code is not linked to any medias Note: When a media Id is given as a input in the Qrcode generator and scanned, the app must validate with the QRcodes present in the database and not with the media Id's | Android ICS | Functional