## Sheet1
Defect ID: | Release/Build # | Open Date: | Close Date: | Problem Area: | Defect or Enhancement: | Problem Title: | Problem Description: | Current Environment: | Defect Type: | Who Detected: | How Detected:
1 | SNP v2.02 | 2015-02-10 |  | Monitor view-Inbox | defect | Inbox monitor , when showing monitor Images the design will disturbs. | check the chrome | Windows7 | UX | QA | Review
2 | SNP v2.02 | 2015-02-10 |  | Micro website | defect | Having a same alias name for the different companies , when we open a Micro website which will opens first |  | Windows7 | functional | QA | review
3 | SNP v2.02 | 2015-02-11 |  | Monitor view-Inbox | defect | Calendar having the last 7 days as showing 8 days | here 4-2-15 to 11-2-15 means how many days . Include end date in calculation (1 day is added) means it will take 7days without 8days | Windows7 | functional | QA | review
4 | SNP v2.02 | 2015-02-17 |  | sptest/mo/media/place | defect | In the last image shown is overlapping. |  | Windows7 | UX | QA | Review
5 | SNP v2.02 | 2015-02-26 |  | Campaign List | Defect | Expired media is adding |  | Windows7 | Functional | QA | Review
8 | SNP v2.02 |  |  | Inbox | defect | Click on monitor image and now click on Link Now |  | Windows7 | functional | QA | Review
9 | SNP v2.02
10 | SNP v2.02 | 2015-03-02 |  | Inbox(live) | defect | Explorer not detects floor and mall type. |  | Windows7 | functional | QA | Review
11 |  | 2015-03-03 |  | monitor-view/inbox | Defect | Filter function is not working |  | Windows7 | functional | QA | Review
12 | SNP v2.02 |  |  | monitor-view/inbox | enhancement | Filter must have a clear option | An option to clear the cache must be available. | Windows7 |  | QA | Review
13 | SNP v2.02 |  |  | monitor-view/inbox | defect | The filter option in Map View does not function |  | Windows7 |  | QA | Review
14 | SNP v2.02 | 2015-03-03 |  | monitor-view/inbox | defect | Monitor images are appearing blank in map view. |  | Windows7 | UX | QA | Review
15 | SNP v2.02 | 2015-03-03 |  | monitor-view/inbox | defect | Incorrect date range is displayed | On selecting the option "Last 7 days" under the calendar option, current date is also taken into account. | Windows7 | functional | QA | Review
16 | SNP v2.02 | 2015-02-04 |  | Monitor - view | Defect | MV - Calendar: Month to Date: Incorrect date range is displayed in calendar | 1. Select Monitor View 2. Select "The Previous Month" option in calendar 3. Select "Month to Date" option in calendar 4. The date range displayed is incorrect Expected: The calendar must display a date range from start date of the current month to current date. | Windows7 | functional | QA | Review
17 | SNP v2.02 | 2015-02-04 |  | Monitor - view/Reports/Pending for monitor | defect | MV - Report - Pending for monitor: Incorrect display for search criteria when no value is given in the 'last days' option. | 1. Go to MV-Reports-Pending for Monitor 2. Delete the value in the 'last days' text box 3. Click on 'Go' option to run a search 4. The message displayed is incorrect Actual: Previous search criteria result message is displayed Expected: A message informing to input the 'Last days' value criteria should be displayed | Windows7 | Functional -Text | QA | Review
18 | SNP v2.02 | 2015-02-04 |  | Monitor - view/Reports/Pending for monitor | defect | MV - Report - Pending for monitor: Cache memory is not clearing | 1. Go to MV-Reports-Pending for Monitor 2. Run a search criteria 3. Select another menu to navigate away from the 'Pending for monitor' page 4. Select 'Pending for Monitor' menu to return back to the page 5. The cache memory is not cleared Actual: Previous search criteria result is displayed Expected: Suggested to clear the cache memory and display the default page | Windows7 | Minor | QA | Review
19 | SNP v2.02 | 2015-02-04 |  | Monitor - view/Reports/Monitor- Overview | defect | MV - Report - Monitor Overview: Initial loading of the page displays all options of street and place media combined. | 1. Login to Owner Account. 2. Go to MV>Reports>Monitor overview 2. Observe that during the initial loading of the page, the map header displays combined options of street and place media. Actual: Displays combined options of street and place media. After the page loads completely the 'street media' header options are displayed. Expected: Display only respective header options of the default selected media | Windows7 | minor | QA | Review
20 | SNP v2.02 | 2015-02-04 |  | Monitor - view/Reports/Monitor- Overview | defect | MV - Report - Monitor Overview: Account Drop down menu Overlapping Color Guide Holder | 1. Go to MV>Reports>Monitor overview 2. Click on Account drop down box. 3. Color guide holder Overlaps Expected: Account drop down menu must display over the Color Guide holder. | Windows7 | Minor | QA | Review
21 | SNP v2.02 | 2015-02-04 |  | Monitor - view/Reports/Monitor- Overview | defect | MV - Report - Monitor Overview - Street Media - Map display- Additional cities data is displayed on selecting 'Billboards' option under Bangalore city. | 1. Go to MV>Reports>Monitor overview 2. Select Street media , City-Bangalore , Media Type-Billboards. 3. Click on 'GO' button 4. Additional Cities are displayed on the map. Expected: Map should display only city related data. | Windows7 | Minor | QA | Review
22 | SNP v2.02 | 2015-02-04 |  | Monitor - view/Reports/Shared Image | defect | MV - Report - Shared Image: Shared image does not get updated when the date range is changed. | 1. Go to MV>Reports>Shared Image 2. Select any Shared Email. 3. Change the Date Range in Calendar 4. Shared Images Data does not get Updated Expected: Shared Images Data should be Update as per changes made in the calendar. | Windows7 | UX | QA | Review
23 | SNP v2.02 | 2015-02-04 |  | Monitor - view/Reports/Shared Image | defect | MV - Report - Shared Image: Shared media Count does not matches | 1. Go to MV>Reports>Shared Image 2. Check medias in shared email. 3. Select any shared email 4. "showing Medias" not make a sense Expected: Shared imaged Data count Should display Exact in the previous page shown. | Windows7 | UX | QA | Review
24 | SNP v2.02 | 2015-02-04 |  | Monitor - view/Reports/Shared Image | defect | MV - Report - Shared Image: Shared Email showing a Duplicating media ID | 1. Go to MV>Reports>Shared Image 2. Check medias in shared email. 3. Select any shared email 4. Medias shown as duplicate. Expected: Shared images are not shown as duplicate | Windows7 | UX | QA | Review
25 | SNP v2.02 | 2015-03-04 |  | Proposal/Active Proposal | defect | Proposal/active proposal: Active proposal showing Http Status 404 error | 1. Go to Proposals>Active Proposals 2.Click on Create a proposal. 3. Enter the all Valid data. 4. Click on save. 5. Click on ID 6. Http status 404-/sptestlist/ message is displayed Expected: The Proposal must display a Proposal List Page | Windows7 | Functional | QA | Review
26 | SNP v2.02 | 2015-03-04 |  | Proposal/Active Proposal | defect | Proposal/active proposal: Oops! Missing Page Link message is displayed | 1. Go to Proposals>Active Proposals 2.Click on Create a proposal. 3. Enter the all Valid data. 4. Click on save. 5. Click on That Proposal 6. Oops! Missing page link message is displayed Expected: The Proposal must display a Proposal List Page | Windows7 | Functional | QA | Review
27 | SNP v2.02 | 2015-03-06 |  | Proposal/List/Active proposal/actions/Delete | Defect | Edit duration/Multiple delete: Multiple delete option does not working. | 1. Go to Proposals>Active Proposals>Actions>Edit duration. 2.Change the proposal duration and apply 3. Click select all checkbox in the media status popup 4. Select 'delete' from the down box and click on go button. 5. Click 'Save' button 6. medias are not deleted Expected: Medias are should be deleted. | Windows7 | Functional | QA | Review
28 | SNP v2.02 | 2015-03-06 |  | Proposal/List/Active proposal/actions/View Details | Defect | Actions/View Details : Without empty view details popup saves | 1. Go to Proposals>Active Proposals>Actions>View details. 2.Click on 'edit' button 3. Clear the description 4.Click on save . Actual: Without any description notes saving. Expected: Save Button Should be disable.
29 | SNP v2.02 | 2015-03-06 |  | Proposal/List/Active proposal/add street media/media Explorer | Defect/performance | Media Explorer: Adding a street media Explorer is not responding. | 1. Go to Proposals>Active Proposals>Add street media. 2.Select "city" as Bangalore and "media Type" as Billboards. 3. click on Go button. Actual: Media Explorer not responding at all. Expected: all the medias for selected city should be display.
30 | SNP v2.02 | 2015-03-09 |  | Campaign/Active campaigns/Create campaign/Share with | Defect | Create new Campaign/Share With: | 1. Go to Campaign>Active campaign>create new campaign> 2.Enter a email Id to share. 3.Enable the auto share option. 4. Create a Campaign. 5. Add a media to the campaign. 6. Go to Monitor view and monitor the media. Actual: The monitored details doesn't get shared with the email ID shared in campaign. note: As it is not shared the shared icon is not updated. Expected: The Monitored media details must appear in the inbox of the shared account (email id) and the 'share icon' color must get updated to green
31 | SNP v2.02 | 2015-03-09 |  | Campaign/Active campaigns/Create campaign | Defect | Create new Campaign/Campaign Name or Client: String length is not defined. | 1. Go to Campaign>Active campaign>create new campaign> campaign name. 2. Enter a String length of 25 Characters. 3.Create a campaign with valid details. Actual: Undefined ID is displayed in the newly added campaign details. Expected: User not be able enter more then 25 characters. or An error message must be displayed when the string length surpasses the defined length. Note: Currently on refreshing the Active Campaign page, the row displaying the undefined ID details is not displayed.
32 | SNP v2.02 |  |  | campaign/campaign Id/media/list/Add place or street media/Media Explorer | Defect | Media Explorer: 'Select media duration' popup window is not displayed on clicking photo view. | 1. Go to Campaign>Active campaign. 2.Click on a campaign name or ID. 3. Click on add a Street or Place media. 4. Select the all valid details click on go. 5.Click Photo view option. 6. Click on any media. Actual: 'select media duration' popup is not displaying. Expected: 'select media duration' popup should display. Notes: Its defects also in the place medias floor view.
|  | 2015-03-16 |  |  |  |  | 1. Go to MV>Inbox>Map view 2. Use the scroll bar to scroll down 3. Observe that the account menu header gets hidden
|  | 2015-03-16 |  |  | Defect | MMS:Monitor view>Inbox:" Go " button is object overlapped in map view. | 1. Monitor view>Inbox: 2. Click on map view. 3. Select the calendar. 4. Enter the start date and end date. 5.scroll up the page. Actual: "Go" button object overlapped with map.. Expected: it should not overlap. |  | small
|  | 2015-03-16 |  |  | Defect | MMS:Monitor view>Inbox: "link now" is not working | 1. Go to monitor view>Inbox: 2.Select any monitor (gps enabled/no gps) . 3. Click on image. 4.click on link now. Actual: The 'link now' link is not functional Expected: On clicking the 'Link now' link, the user must be taken to 'linking the monitor to the respective media' window |  | Normal
|  | 2015-03-16 |  |  | Defect | MMS:Monitor view>Inbox: The actions menu overlaps the monitor images. | 1. Go to monitor view>Inbox: 2.Select any monitor. 3. Click on actions. 4.Move the cursor on the monitor image near by the actions menu. Actual: The actions menu overlaps the monitor preview images Expected: The menu must be under the preview image and not overlap the preview images.
|  | 2015-03-16 |  |  | Defect | MMS:Monitor view>Reports> Pending for monitor: No "loading" message appears | 1. Go to Monitor view>reports: 2.Click on pending for monitor: Actual: "loading" message is not displayed while the page loads. Expected: The loading message must be displayed while the page loads. |  | Normal
|  | 2015-03-16 |  |  | Defect | MMS: Medias: "select area" text box appears twice on logging in first time. | 1. Login as a first time user(Clear the cache). 2. Click on "medias" in the menu. Actual: "Select area" text box is displayed twice. Expected: The textbox appearing below the 'select area' option must not appear |  | Normal
|  | 2015-03-17 |  |  | Defect | MMS:Inventory>Dashboard: Text should be displayed as "Media overview" in place of "Inventory overview" | 1. Go to Inventory>Dashboard Actual: 'Media overview' text is displayed in the dashboard (Below the occupancy overview graph) Expected: Text should be display as "Inventory overview" |  | Small
|  | 2015-03-17 |  |  | Defect | MMS:Inventory>dashboard:Monitor overview section in dash board , Clicking on street button all media type and cities are not displayed in the "MediaOverViewChartHolder". | 1. Go to Inventory>Dashboard 2. Select media overview 3. Click on 'Place' button 4. Click on 'Street' button Actual: Not displays 'Traffic Umbrella' in the media type and some cities are missed in 'cities' chart in the "MediaOverViewChartHolder" Expected: available 'cities' and 'media type ' should be display in the chart. |  | Small
|  | 2015-03-17 |  |  | Defect | MMS: Inventory overview: Not updated the 'Showing unit of media inventory as on today Show NO_OF (ddb) entries' in the data table. | 1. Go to Inventory>Reports: 2. Click on Inventory overview 3. Select street or place media and Unit or price or size in ddb . 4. Click on Go. 5.Select 'Showing unit of media inventory as on today Show25 entries' Actual: Data table not updated when selecting the 'Showing unit of media inventory as on today Show NO_OF (ddb) entries' in the data table. Expected: data table should be update when selecting 'Showing unit of media inventory as on today Show NO_OF (ddb) entries' . |  | Normal
|  | 2015-03-17 |  |  | Defect | MMS:Inventory overview: Data not displayed in the Excel sheet (MS-Excel) and data not aligned correctly in the excel sheet (Open Office) | 1. Go to Inventory>Reports: 2. Click on Inventory overview 3. Select street or place media and Unit or Price Or Size in ddb . 4. Click on Go. 5.Click on Export to excel Button. 6.Open the excel sheet in MS-Excel or Open office. Actual: Exported data is not displayed in excel sheet(MS-Excel) and data is not aligned correctly(Open office) Expected: Exported data should be correctly display and aligned in all excel sheets. |  | Normal
|  | 2015-03-17 |  |  | Defect | MMS: Inventory Overview: Data in the table not updated to the place media | 1. Go to Inventory>Reports: 2. Click on Inventory overview 3. Select place media . Actual: Clicking on place media displayed a message of " No floor available" Expected: The default data in the table should be updated to the place media data. |  | Normal
|  | 2015-03-17 |  |  | Defect | MMS: Inventory Overview: Data in the table not updated to the Street media | 1. Go to Inventory>Reports: 2. Click on Inventory overview 3. Select place media in ddb 4. Select street media in ddb Actual: When changing the media type as street media data is not updated in the data table. Expected: Default data of street media should be update in the data table. |  | Normal
|  | 2015-03-23 |  |  | Defect | MMS:Medias>Media manager>Calendar: Previous date is included while displaying the number of active days status of the media | 1. Go toMedias>Media manager 2. Select any live/pending media (associated with a active campiagn). 3. Click on Calendar Icon. Actual: Previous date is included while displaying the number of active days status of the media . Expected: Previous date must not be taken into account while displaying the active days of the media Note: For example if the duration set for a media is from 21th Apr2015 to 30april2015, on viewing the calendar the active days of the media is displayed as: 20april to 30april
|  | 2015-03-24 |  |  | Defect | MMS: Image view: The calendar scrolls under the image frame. | 1. With the user logged in, go to Search Screen(2nd screen). 2. Enter the Search Criteria. 3. Click on Image View. 4. Select any media. 5. Move the cursor to the bottom of the selected media frame. Actual: The calendar which appears scrolls under the frame of the selected media and the user cannot view details of the first few months. Expected: The user must be able to view the complete calendar.
|  | 2015-03-24 |  |  | Defect | MMS: Inventory mediawise: The mall dropdown list needs to be aligned correctly | 1. Go to Inventory>Reports>Inventory mediawise 2. Select media type as place media. 3. Click on the mall dropdown list Actual: The dropdown list is not correctly aligned Expected:Dropdown list must be correctly aligned
|  | 2015-03-24 |  |  | Defect | MMS: Inventory mediawise: The Header of the page 'Reports>Inventory mediawise' must be changed to "Reports>Occupancy Media Wise" | 1. Go to Inventory>Reports>Inventory mediawise Actual: Header of the page of the name 'Inventory mediawise ' is displayed. Expected: The Header of the page 'Reports>Inventory mediawise' must be changed to "Reports>Occupancy Media Wise" Note: 1. On clicking "inventory media wise", the address bar of the explorer displays "http://www.snapooh.com/mo/report/inventory/dashboard#OccupancyMediaWise?mCategory=1&cityId=230&mediaTypeId=-1&areaId=-1&startDate=March%2001,%202015&endDate=March%2030,%202015" 2. On clicking on any media in the table, the header on the loading page changes to "Report > Occupancy Media Wise > Media Overview"
|  | 2015-03-24 |  |  | Defect | MMS: Inventory mediawise> Media Overview: Selecting of the calendar it is redirecting to the Inventory mediawise page | 1. Go to Inventory>Reports>Inventory mediawise> Media Overview: 2. Select the Calendar. 3. Click on any date. Actual: the page is redirecting to the inventory mediawise page. Expected: the data should be update when date is updated.
|  | 2015-03-31 |  |  | defect | MMS:- Monitor view>Inbox: Selecting city ddb in media explorer the monitor inbox page is scrolling down. | 1. Go to Monitor view>Inbox. 2. Select GPS disabled street media monitor. 3. click on link now (media linking). 4. Selct city ddb Actual : The monitor inbox page is scrolling down. Expected: The monitor inbox page stay with the explorer popup and page should not go to scroll sown.
|  | 2015-03-31 |  |  | defect | MMS:- Monitor view>Inbox: Media details are not reflecting in the selecting Monitor image in the monitor 'inbox Detailed View' window | With GPS on/off 1. Go to Monitor view>Inbox 2. Select any unlinked monitor(media) 3. Click on link now(Media linking). 4. link a media to the monitor 5. Click on the linked monitor Actual: In the detailed view window observe that the link media details are not updated. Expected: Once the message confirming the linking of the media appears, the media details must get updated dynamically in the detailed view window. Note: currently, the media link detail is updating only on refreshing the page
|  | 2015-03-31 |  |  | defect | MMS:- Monitor view>Inbox>link now(street media)>media Explorer: Selecting snapooh id the media explorer is redirecting to the 'monitor inbox page'. | With GPS Off 1. Go to Monitor view>Inbox 2. Select any unlinked monitor( street media) 3. Click on link now(Media linking). 4. select city and media type. 5. Click on go. 6. click on any medias snapooh Id. Actual: Clicking on snapooh id it is redirecting to monitor inbox page without linking the media. Expected:Selecting snapooh id "linking Media Popup" should display.

## APRIL-MONTH
Defect ID: | Release/Build # | Open Date: | Close Date: | Problem Area: | Defect or Enhancement: | Problem Title: | Problem Description: | Current Environment: | Defect Type: | Who Detected: | How Detected:
|  | 2015-04-02 |  |  | Defect | MMS:Mediadetail: The availability calendars "Progress bar Holder" is over lapping. | 1. Go to medias. 2. Select a media. 3. Click on calendar Icon. 4. Modify the date(here calendar not affecting ). 5. Go to search page(2nd Screen). 6. Enter the details in search filter. 7. Click on go . 8. Select a media. 9. click on full details button. Actual: The availability calendar "progress bar holder" is overlapped. Expected: The availability calendar should display as calendar modified (above step 4). Note: This defect is occurring for rare medias. so please refer for this media Id:12242 | Windows | Normal
|  | 2015-04-02 |  |  | Defect | MMS: Inventory: selecting the previous month in the(First Click) Calendar is displaying the current month dates also. | 1. Go to Inventory>Calendar. 2. Click on "the Previous month"(First click). Actual: The previous month data with current month date also included. Expected: The data should display only for the previous month. Note: Please check for Dash board ,Inventory mediawise,Occupancy timeline ,overview and both the heat maps. . | Windows | Normal
|  | 2015-04-02 |  |  | Defect | MMS: Inventory:Non location based place media are not displayed. | 1. Go to Inventory>Inventory media wise or Vacancy list or Occupancy time line . 2.Select place media. 3. Click on go. Actual: Non location based place medias are not displaying. Expected: Location based and no location based both the medias should display. |  | Normal
|  | 2015-04-02 |  |  | Defect | MMS:Inventory>Reports>vacancy list: The size of the medias not correctly defined. | 1. Go to Inventory>Reports> Vacancy list . 2.Enter all the valid details in Search Filter . 3. Click on go. Actual: In the data table media Size is shown as undefined Expected: The media size should be shown in the data table with Inches or Sq.ft. Note: Please check the Inventory media wise for Size is not shown in Inches OR Sq.ft |  | Normal
|  | 2015-04-02 |  |  | Defect | MMS:Inventory>Reports:Occupancy overview: Data is not displayed for the selecting date as today in the calendar. | 1. Go to Inventory>Reports> Occupancy Overview . 2.Enter the place media with valid city and media type. 3. Click on go. 4. select calendar as today(verify the medias in the table). 5. Select Calendar as last 7days Actual: In last 7 days shown the "current date" date and when selecting date as "Today" the data wont display. Expected: Selecting on the calendar for right data , it should display a correct data in the table. |  | Normal
|  | 2015-04-02 |  |  | Defect | MMS:Inventory>Reports:Occupancy overview: Medias count as shown not displayed correctly . | 1. Go to Inventory>Reports> Occupancy Overview . 2.Enter the place media with valid city and media type. 3. Click on go. Actual: Displaying a message as "Showing 15 Medias" but actually displays 5 medias Expected: all the medias should display for selected citywide. Note: Here we are not showing the medias , we are showing city wise medias. , so please change the "showing medias " instead "showing cities" |  | Normal
|  | 2015-04-07 |  |  | Defect | MMS:Inventory>Reports>vacancy list or Inventory media wise or Vacancy list : The size(dimension) of the medias are not defined correctly. | 1. Go to Inventory>Reports>vacancy list: 2.Enter all the valid details in Search Filter(street/place) . 3. Click on go. Actual: the dimensions of the media size is not displayed correctly. Expected: the dimensions of the media size should display as "Inches" OR "Sq.ft" Note: The same defect is observed in the "Inventory media wise /Vacancy list " |  | Small
|  | 2015-04-07 |  |  | Defect | MMS:Inventory: Occupancy Overview: the data in the "occupancy Overview Time Line GraphId" is hiding | 1. Go to Inventory >Reports>Occupancy overview: 2. Click on "inbxSprit minimizer"(left Nav). Actual: The data shown now in the "occupancy Overview Time Line GraphId" Expected : The data should display correctly in "occupancy Overview Time Line GraphId" as well as when clicking on |  | Normal
|  | 2015-04-07 |  |  | Defect | MMS:Inventory: Occupancy Overview: The message displayed in the header "Showing___Medias" is in correct. | 1. Go to Inventory >Reports>Occupancy overview: 2. Select Places media and media type in the search filter. 3. Click on Go . Actual: The message is displayed in the header "Showing__Medias" Expected: The message should be display in the "Showing_Places". Note: Check for Street media and message should display as "Showing_Cities" |  | Small
|  | 2015-04-09 |  |  | Defect | MMS:Proposals>Active Proposal: Converting to the campaign is not working(If all the medias all are available) for Create New Campaign. | 1. Go to Proposals>Active Proposals. 2. Select any proposal. 2. Select actions. 3. Select "Convert to campaign". 5. Click on Create New button. 6. Click on Convert Actual: Displays a alert message of "Conflict" 'This proposal has medias which are conflicting with the period, you should first rectify the conflicts before converting it into a proposal'. Expected : It should be allow to convert proposal to campaign. Note: The Proposal converting to campaign in the "Use Existing "
|  | 2015-04-09 |  |  | Defect | MMS:Proposals>Active Proposal>List(proposal Id)>add street/place>Media Explorer popup Clicking on Snapooh Id is redirecting to proposal list page. | 1.Go to Proposal>Active Proposal: 2. Select Proposal Id 3. Click on add street/place. 4. Enter media Id in the Search field . Click on go. 5. Click on Snapooh ID. Actual: It is redirecting to the Proposal list page. Expected : Media detail page should display for selected media.
|  | 2015-04-09 |  |  | Defect | MMS:Proposals>Active Proposal>List(proposal Id)>add place>Media Explorer popup The Non Location Based Medias are Not displayed in the Media Explorer Popup. | 1.Go to Proposal>Active Proposal: 2. Select Proposal Id 3. Click on add place. 4. Enter the all fields and click on go. Actual: Non location based medias are not displayed in the Media Explorer popup. Expected: Both Location and Non Location Based medias should display in the media Explorer popup.
|  | 2015-04-16 |  |  | Defect
Note on F11: designe102: PUT IT ON STAY

## MMS_V2.03
Defect ID: | Open Date: | Defect or Enhancement: | Problem Title: | Problem Description:
| 2015-05-01 | Defect | Login: Verification of the mail is not working | 1. Signup and login with the valid UN and PWD. 2. Click on verify the email link. 3. Check the mail link and click on verify. Actual: The empty screen of is displayed. Expected: The page is redirect to Snapooh site and say your mail verified.
| 2015-05-01 | Defect | Media Manager: Search filter is not working. | 1. go to Medias. 2. Select any city in "City" drop down.. 3. Select area. 4. Click on go. Actual: All the medias are displayed with the default city. Expected: Only selected cities medias should display.
| 2015-05-01 | Defect | Proposal: same media in the different proposals are converted to a campaign. | 1. Go to proposal>active proposal. 2. Enter Create a Two different proposals with same name and same date. 3. add a same media to the both proposals. 4. Convert the one proposal to campaign. 5. Convert another proposal to the campaign. Actual: The second proposal also converted to the campaign. Expected: When converting a 2nd proposal should show a conflict msg.
| 2015-05-01 | Defect | Proposal: "Converting proposal into campaign" in using Existing campaign chosen campaign is not selected. | 1. Go to Proposal>Active proposal: 2. Select any proposal with having a medias. 3. Select " converting to campaign " in actions dropdown . 4. Select "Use Existing" . 5. Select any one Existing campaign and Click on Convert. 6. go to closed won > Converted Campaign> associated campaign. Actual: The associated campaign with the closed won does not matches. Converting proposal into campaign. Expected: Selected associated campaign only should display.
| 2015-05-01 | Defect | Monitor View>Reports>Pending for Monitor: The last days field is accepting for the "Zero" and "Negative ' values | 1. Go to Monitor View>Reports>Pending for Monitor: 2. Enter a "Zero" or "Negative (-4)' in days field. 3. Click on Go. Actual : The Message is displayed with the entered Zero and Negative date Value. Expected: The data should not display for the above conditions.
| 2015-05-01 | Defect | Inventory and Monitor View: Whenever Selecting the place media " No floor available" Message is displayed | 1. Go to Monitorview> Reports: 2. Select MediaWise. 3. Select place media In place drop down . Actual :" No floor available" Message is displayed. Expected: Whenever selecting a place media the message should not display. Note: Please check Monitor View: Mediawise, DateWise,Pending for monitor,monitor overview. Inventory:Occupancy Media Wise, Vacancy Overview,Vacancy List, Occupancy Time Line,Occupancy Overview.
| 2015-05-01 | Defect