## Sheet1
CINEMA-CMS
Address: http://192.168.1.10:8080/cms_test/admin/media/cinema/screen
DATE | 2015-06-24
Module | Open Date: | Defect or Enhancement: | Problem Title: | Problem Description: | Defect Type:
MOVIE-language |  |  | Movie Language:duplicate movie languges are accepting | Movie Language: 1. Select a new and Enter a language name (Ex:Kannada). 2. Again Enter a same language in New field. Actual: Duplicate language names are created in the "List View" language tab. Expected: It should not be accept the creating a duplicate language.
MOVIE-language |  |  | Movie Language: Deleting a Language name in the list view ,The id of the language is not arranged correctly | 1. Go to Movie-language>List View. 2. Select a language and click on delete and confirm. Actual: The id of the language is not ordered or arranged correctly Expected: Deleting a language id , the previous id of the language should replece.
Cinema Movie Languages(s) |  |  | 1.List view: No data displayed in the list view after selecting a movie | 1. Go to Cinema Movie Languages(s)>List view: 2. Select a movie and click on search language. Actual "data Found" Message is displayed. But no data is displayed Expected: It should display a movie with its language. Note: In the list view tab "false" text is displayed
Cinema Movie Gener(s) |  |  | List View: all the movie generes displayed for selecting a movie in the list view | 1. Go to Cinema Movie Genere(s)>List view: 2. Select a movie and click on search Genre(s). Actual: all the movie generes are displayed. Expected; It should display only a selected movies 'genre'.
Movie Schedule |  |  | List View:the updated "Movie schedule" data is not displayed in the List view tab | 1. Go to Movie Schedule>New. 2. Enter the all valid data and click on add button. 3. Select List view tab. Actual: the newly uopdated movie schedule data is not updated. Expected: It shoud display the update movie schedule list.
Theatres |  |  | List View: Edit: When Edit of the theatre is done , the edited theatre deletes | 1. Go to Theatres> List View. 2. Select a theatre and click on edit. 3. Modify the detail and click on submit. Actual: The modified theatre is deleted from the list. Expected: The theatre should not delete and the modified data should update.
Note on A6: designe102: same bug for Movie Gener(s)
Note on A7: designe102: Same bug for Movie Gener(s) and Movie Occupancy(s)